## Sheet1
Components | Description | Task Type | Stream Dependencies | Prerequisites / Inputs | Tasks | Output / Deliverables | Time Estimates
Plan & Design | Define a Roadmap to establish the level of DevSecOps Maturity through the COE. | Planning and Documenting | [5 empty] | what are the current SARB maturity level and process established?
| Plan and implement target maturity levels for DevOps | Assessment and Procurement
| Design the architecture for the DevSecOps pipeline for R1 and target maturity. | Architecture
DevOps Processes | Define and document the DevSecOps processes | Documentation
| Align DevSecOps with the bi-modal (Agile/Waterfall) Delivery Methodology | Architecture
| Define and document the key drivers, principles, and standards that are required for DevSecOps. | Documentation | [5 empty] | Currently what are they key drivers principles, and standard followed in SARB.
| Document and Integrate to organizational standards, processes, and tooling. (release management, change management, testing) | Documentation, Design and Implement | [5 empty] | SARB what are they standards process are following. What are the approach are following Release management & change management What are the tools are integrating for testing?
| Integrate DevSecOps practice with SARB security standards and processes | Design and Implement | [5 empty] | What are the current security standards followed within SARB
| Identify and define business KPI’s/metrics/alerts for all the phases of the DevSecOps pipeline. | Documentation | [5 empty] | What are the current KPI/metrics/standards/alerts are followed within SARB.
| Assess the existing DevSecOps tools available and determine the toolchain required to complete the stack for the Continuous Integration/Continuous Delivery platform. | Documentation and Architecture
| Define and document the DevSecOps reference architecture Commission and configure the toolchain for the DevSecOps practice | Documentation, Architecture, Configure and Implement
| Install, configure and integrate the DevSecOps pipeline with existing SARB tools (provisioning) | Install, Configure and Integrate | [5 empty] | Can isolation require between agile and water fall environment to accomplish DevSecOps scanning.
| Define and Implement technology KPI’s/SLA metrics/alerts and relevant telemetry | [6 empty] | What is the time of SLA and who are the parties of alerts What are the types of alerts Infra alerts
| Align and document of DevSecOps application stack tiering as per SARB standards required | [6 empty] | We need SARB standards that are align for DevSecOPS application
| Design and implement fit for use Dashboards required for the DevSecOps pipeline | [6 empty] | What are the tools want to see in dashboards irrespective of each tool
| Implement increased automation and optimization across the DevSecOps pipeline | [6 empty] | I am not able to understand the point
Support and Maintenance | Define and document the COE Support structure to sustain the DevSecOps practice | [6 empty] | Need to provide the support structure details
| Provide support during and post-implementation for toolchain and processes | [6 empty] | Need to get the confirmation with the manager
Capacitating | Define and document the governance and roles required to operate and sustain the DevSecOps pipeline | [6 empty] | Once everything setup is completed what are the roles required and pipeline to be sustain
| Define and document the DevSecOps RACII Matrix with stakeholder analysis. | [6 empty] | Need to know matrix information
| Define and document the change management with new processes. | [6 empty] | Currenlty what are the change management process are following in SARB(If it is freeze movement )
| Resource and operate the DevSecOps environment for the duration of implementation. | [6 empty] | Could you help me understand and what is the mean of point
| Knowledge transfer to internal SARB tech staff to ensure continuity. | [6 empty] | What should the duration of KT Plan as per the SARB standards What is the SARB current process in place of governance standards and tools.